## PROBLEMS AND RISK PRIORITY
Item Number | Unique ID | Problem | Priority | Proposed Action | PC informed | Date | Date resolved
3 | Playing field 1 | Hogweed reported by M.O.P | RISK 3 | Advised removal needs to be done during the growing season, June, PC to srrange contractor | 2021-10-18 | 2021-10-18
5 | Playing field 2 | Cracked manhole in Tennis club track | RISK 2 | Repair - PC to manage | PPC | C/F
6 | Playing field 3 | Cricket shed, missing planks | RISK 2 | PC managing | MANGING | 2021-05-10
7 | VH car park 1 | Parking bays | RISK 2 | Re mark - PC to manage | PPC | C/F
8 | VH car park 2 | Over hanging branched & brambles west border | RISK 3 | Cut back over hanging limbs - PPC to manage | PPC | C/F
9 | Green 1 | Track flooded, not into Kimber cottages | RISK 2 | VHM to momitor, flooded due to heavy rain | 2022-02-28 | On going
| Green 2 | Ally by pond overgrown | Risk 2 | PPC to manage
10 | Green 3 | Several fallen trees | RISK 2 | PPC to manage | PPC | C/F
11 | Green 4 | Garden waste x 3 dumped in woods | RISK 2 | PPC to manage, 21/3/2022 grass cuttings dumped, 30/5/2022 garden waste | AG & RJ 6/9/21 | C/F
12 | Green 5 | 2 loose bricks residents side | RISK 2 | VHM to monitor | PPC | C/F
13 | Green 6 | Edge coming away, advisory | RISK 2 | VHM to monitor | N.SATCHELL & PPC | C/F
| C/F = | ITEMS CARRIED FORWARD FOR OLD STYLE RA'S, PRE APRIL 2021
| RISK 1 | IMMPOBABLE
| RISK 2 | REMOTE
| RISK 3 | OCCASSIONAL (ACTION WITHIN 6 MONTHS)
| RISK 4 | PROBABLE (ACTION WITHIN 3 MONTHS)
| RISK 5 | HIGH RISK (IMMEDIATE ACTION)

## Allotments
RISK ASSESSMENT - ALLOTMENTS MAY-DEC 2022 |  |  | SUGGESTED EXAMPLES
Area | Items to Be Checked | 2022-05-30 | Issue | Item Number | Date Notified | Date Resolved
Main Footpaths | Hidden Potholes | ü
| Litter, Rubbish and General Waste | ü
| Obstructions | ü
Raised Beds | Edges Clearly Visible | ü | PATHS NEED STRIMMING, RJ & JB SORTED |  | 2022-05-30 | 2022-06-03
Water Butts | Check for Hazards | ü
Wooded Area | Uneven Ground | ü
| Fallen Trees Branches | ü
| Overhanging Branches | ü
| Brambles / Nettles | ü
| Litter, Rubbish and General Waste | ü
| Wasp / Bee Nests | ü
Stream | Warning Signs and Hazards | ü
| Bank Hazards | ü
| Flooding | ü
Benches | Safe To Use | ü
Gates | Good Order | ü

## Playing Field
RISK ASSESSMENT - PLAYING FIELD MAY-DEC 2022
Area | Items to Be Checked | 2022-05-30 | Issue | Item number | Date Notified | Date Resolved
Field | Trips / Slip Hazard | ü
Litter On Field | Collect And Remove | ü
Cricket Square | Tap | ü
| General | ü
Cricket Nets | General | ü
Cricket Screen | Secured And Safe | ü
Public Goals | Fit For Purpose | ü
Club Goals | Posts / Nets | ü
Hedges / Trees | Overhanging Branches | ü
Trees | Fallen Trees / Branches | ü | Low hanging broken branch, removed, RJ aware |  | 2022-05-30 | 2022-05-30
All Areas | Brambles / Nettles | û | HOGWEED PC to arrange removal, advised this can't be don't till new growning season in June | Playing field 1 | 2021-10-18
Litter / Hedges | Collect And Remove | ü
Hedges / Trees | Wasp And Bee Nests | ü
Pathways | Trip / Slip / Fall Hazards | ü
Tennis Track | Signage Visible | ü
| Detioration | û | Cracked manhole, | Playing field 2 | C/F
Benches x 2 | Fit For Purpose | ü
Bkt Ball Court | Tarmac Safe | ü
Litter Bins | Clear Overflowing Litter | ü
| Emptied On Schedule | ü
Outbuildings | Vandalism | ü
| Locked And Maintained | û | PC managing | Playing field 3 | 2021-06-01

## Pavilion Car Park
RISK ASSESSMENT - PAVILION CAR PARK MAY - DEC 2022
Area | Items to Be Checked | 2022-05-30 | Issue | Item Number | Date Notified | Date Resolved
Car Park | Car Park Lighting | ü
| Footpath Clear / Safe | ü
| Signage Visible | ü
| Trip Hazards | ü
| Free From Litter | ü
| Litter Bin Maintained | ü
| Overhanging Branches | ü
| Fallen Branches / Trees | ü
| Bollards Safe | ü
| Gates Safe And Locked, when not in use | ü
| Recycling Compound | ü

## Village Hall Car Park
RISK ASSESSMENT - VILLAGE HALL CAR PARK MAY - DEC 2022
Area | Items to Be Checked | 2022-05-30 | Issue | Item number | Date Notified | Date Resolved
Car Park | Bay Marking | û | Many faded, Risk 2 | VH car park 1 | 2019-11-01
| Car Park Lighting | ü
| Footpath Clear / Safe | ü
| Trip Hazards | ü
| Hedges Safe | ü
| Free From Litter | ü
| Litter Bin Maintained | ü
| Overhanging Branches | û | Over hanging branches & brambles west border | VH car park 2 | 2021-01-07
| Fallen Trees / Branches | ü
ü

## Green and Pond
RISK ASSESSMENT - GREEN AND POND MAY - DEC 2022
Area | Items to Be Checked | 2022-05-30 | Issue | Issue | Item Number | Date Notified | Date Resolved
GREEN | Hidden Potholes | ü
| Litter & Rubbish | ü
| Manhole Cover | ü
| Trees/Shrubs/Hedges | ü
| Grass Length | ü
| Spilt Rubbish By Bin | ü
WOODS | Uneven Paths | ü |  | Monitoring of track for flooding continued | Green 1 | 2022-02-28
| Overhanging Branches | û |  | Ally by pond overgrown | Green 2
| Fallen Trees / Branches | û |  | Several fallen trees, Risk 2, Tree leaning/snapped? FS to assess and report back. NS aware 15/11/21 | Green 3 | 2021-01-06
| Brambles / Nettles | û |  | Garden waste x 3 dumped in wooded area, VHM to monitor, Grass cuttings 21/3/2022, 30/5/2022 garden waste | Green 4 | 2021-09-06
| Dropped Litter/ Rubbish | ü
| Wasps / Bee Nests | ü
POND | Life Aid & Signage | ü | Signs Missing
| Perimeter & Fence | ü
| Trip/Slip/Fall Hazards | ü
| Gully Edges | ü
| Brick Wall | ü |  | 2 loose bricks residents side, Risk 2 | Green 5 | 2020-09-03
| Wooden area | ü
Benches | Fit For Purpose | ü
Bandstand | Electricity Supply Off/On | ü
| Electrics Undamaged | ü
| Fit To Use | ü
| Path Safety | ü |  | Edge coming away, advisory, Risk 2 | Green 6 | 2020-09-03
Bridge | Railings | ü
| Base Of Bridge | ü
ü
Benches | Safe To Use | ü