## PROBLEMS AND RISK PRIORITY
Item Number | Unique ID | Problem | Priority | Proposed Action | PC informed | Date | Date resolved
| Playing field 1 | PPC shed resting on concerte blocks | RISK 2 | PPC aware, JB to arrange a permiment fix | 2023-09-05 | 2023-09-18
| Playing field 2 | Bags of rubble by Archery's container | RISK 2 | Archery to remove, PPC to request | 2023-10-04
| Playing field 3 | Astro turf run up to practice nets badly split | RISK 2 | Cricket aware, cricket to repair | 01/06/2023, RJ
| Playing field 4 | Path round PAV crumbling, always had dips but deteriated over last month. | RISK 2 | Path to be patched, PC to manage. | 04/07/2023. RJ AND AE
| Playing field 5 | 4 loose slabs outside electrical room | RISK 2-3 | Hazzard taped, Slabs to re-concreted, PC to manage | 2023-07-04
4 | VH car park 1 | Parking bays | RISK 2 | Re mark - PC to manage | PPC | C/F | CIL?
| VH car park 2 | Loose slab by bridge | RISK 2 | To be recermented - JB aware and hopes to fix | 2023-07-04
6 | Green 1 | Track flooded, not into Kimber cottages | RISK 2 | VHM to momitor, flooded due to heavy rain | 2022-02-28 | On going
9 | Green 2 | Edge coming away, advisory | RISK 2 | VHM to monitor | N.SATCHELL & PPC | On going
| Green 3 | Pond edge exposed since rushes have been removed | RISK 3 | PPC to consider if edge should be fenced. | 2023-09-05
| C/F = | ITEMS CARRIED FORWARD FOR OLD STYLE RA'S, PRE APRIL 2021
| RISK 1 | IMMPOBABLE
| RISK 2 | REMOTE
| RISK 3 | OCCASSIONAL (ACTION WITHIN 6 MONTHS)
| RISK 4 | PROBABLE (ACTION WITHIN 3 MONTHS)
| RISK 5 | HIGH RISK (IMMEDIATE ACTION)

## Allotments
RISK ASSESSMENT - ALLOTMENTS 2023 | [12 empty] | SUGGESTED EXAMPLES
Area | Items to Be Checked | 2023-01-03 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 2023-05-03 | 2023-06-01 | 2023-07-03 | 2023-07-31 | 2023-09-05 | 2023-10-03 | 2023-10-31 | Issue | Item Number | Date Notified | Date Resolved
Main Footpaths | Hidden Potholes | bar: 2023-01-03 to 2023-10-31
Litter, Rubbish and General Waste | bar: 2023-01-03 to 2023-10-31
Obstructions | bar: 2023-01-03 to 2023-10-31
Raised Beds | Edges Clearly Visible | bar: 2023-01-03 to 2023-10-31
Water Butts | Check for Hazards | bar: 2023-01-03 to 2023-10-31
Wooded Area | Uneven Ground | bar: 2023-01-03 to 2023-10-31
Fallen Trees Branches | bar: 2023-01-03 to 2023-10-31
Overhanging Branches | bar: 2023-01-03 to 2023-10-31
Brambles / Nettles | bar: 2023-01-03 to 2023-10-31
Litter, Rubbish and General Waste | bar: 2023-01-03 to 2023-10-31
Wasp / Bee Nests | bar: 2023-01-03 to 2023-10-31
Stream | Warning Signs and Hazards | bar: 2023-01-03 to 2023-10-31
Bank Hazards | bar: 2023-01-03 to 2023-10-31
Flooding | bar: 2023-01-03 to 2023-10-31
Benches | Safe To Use | bar: 2023-01-03 to 2023-10-31
[8 empty] | ü | ü | ü | ü | ü
Gates | Good Order | bar: 2023-01-03 to 2023-10-31

## Playing Field
RISK ASSESSMENT - PLAYING FIELD 2023
Area | Items to Be Checked | 2023-01-03 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 2023-05-03 | 2023-06-01 | 2023-07-03 | 2023-07-31 | 2023-09-05 | 2023-10-04 | 2023-10-31 | Issue | Item number | Date Notified | Date Resolved
Field | Trips / Slip Hazard | [11 empty] | PPC SHED RESTING ON CONCRETE BLOCKS | Playing field 1 | 2023-09-18 | bar: 2023-01-03 to 2023-10-31
Litter On Field | Collect And Remove | [11 empty] | Bags of rubble by new archery shipping container | Playing field 2 | bar: 2023-01-03 to 2023-10-31
Cricket Square | Tap | bar: 2023-01-03 to 2023-10-31
General | bar: 2023-01-03 to 2023-10-31
Cricket Nets | General | [11 empty] | ASTRO TURF RUN UP SPLIT, KS AWARE | Playing field 3 | 2023-06-01 | bar: 2023-01-03 to 2023-10-31
Cricket Screen | Secured And Safe | bar: 2023-01-03 to 2023-10-31
Public Goals | Fit For Purpose | bar: 2023-01-03 to 2023-10-31
Club Goals | Posts / Nets | [11 empty] | GOALS REMOVED, BUT NEED SECURING |  | 2023-05-03 | NEW SEASON STARTED | bar: 2023-01-03 to 2023-10-31
Hedges / Trees | Overhanging Branches | bar: 2023-01-03 to 2023-10-31
Trees | Fallen Trees / Branches | bar: 2023-01-03 to 2023-10-31
All Areas | Brambles / Nettles | bar: 2023-01-03 to 2023-10-31
Litter / Hedges | Collect And Remove | bar: 2023-01-03 to 2023-10-31
Hedges / Trees | Wasp And Bee Nests | bar: 2023-01-03 to 2023-10-31
Pathways | Trip / Slip / Fall Hazards | [11 empty] | Path round PAV, is now crumbling, always had dips in it but deteriated over the last month. | Playing field 4 | 2023-07-04 | bar: 2023-01-03 to 2023-10-31
[13 empty] | 4 loose slabs outside electrical room, hazzard taped PPC aware, JB to look at. | Playing field 5 | 2023-07-04 | bar: 2023-04-04
Tennis Track | Signage Visible | bar: 2023-01-03 to 2023-10-31
| Detioration | [11 empty] | Cracked manhole, Specialised contractor to assess |  | C/F | 04/10/2023 C LEWERY | bar: 2023-01-03 to 2023-10-31
Passing bays in good order, installed 4/10/2023 | bar: 2023-10-04 to 2023-10-31
Benches x 2 | Fit For Purpose | bar: 2023-01-03 to 2023-10-31
Bkt Ball Court | Tarmac Safe | bar: 2023-01-03 to 2023-10-31
Litter Bins | Clear Overflowing Litter | bar: 2023-01-03 to 2023-10-31
Emptied On Schedule | bar: 2023-01-03 to 2023-10-31
Outbuildings | Vandalism | bar: 2023-01-03 to 2023-10-31

## Pavilion Car Park
RISK ASSESSMENT - PAVILION CAR PARK 2023
Area | Items to Be Checked | 2023-01-03 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 2023-05-04 | 2023-06-01 | 2023-07-03 | 2023-07-31 | 2023-09-05 | 2023-10-04 | 2023-10-04 | Issue | Item Number | Date Notified | Date Resolved
Car Park | Car Park Lighting | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Footpath Clear / Safe | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Signage Visible | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Trip Hazards | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Free From Litter | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Litter Bin Maintained | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Overhanging Branches | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Fallen Branches / Trees | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Bollards Safe | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Gates Safe And Locked, when not in use | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Recycling Compound | ü | ü | ü | û | ü | ü | û | ü | ü | û | ü

## Village Hall Car Park
RISK ASSESSMENT - VILLAGE HALL CAR PARK 2023
Area | Items to Be Checked | 03/0102023 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 04/05/023 | 2023-06-01 | 2023-07-03 | 2023-07-31 | 2023-09-05 | 2023-10-04 | 2023-10-31 | Issue | Item number | Date Notified | Date Resolved
Car Park | Bay Marking | û | û | û | û | û | [6 empty] | Many faded, Risk 2 | VH car park 1 | 2019-11-01 | bar: 2023-06-01 to 2023-10-31
| Car Park Lighting | ü | ü | ü | ü | ü | [6 empty] | Loose slab by bridge | VH car park 2 | 2023-07-04 | bar: 2023-06-01 to 2023-10-31
| Footpath Clear / Safe | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-10-31
| Trip Hazards | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-10-31
| Hedges Safe | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-10-31
| Free From Litter | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-10-31
| Litter Bin Maintained | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-10-31
| Overhanging Branches | û | û | û | ü | ü | [6 empty] | Over hanging branches & brambles west border, cleared by working party |  | 2021-01-07 | 2023-03-18 | bar: 2023-06-01 to 2023-10-31
| Fallen Trees / Branches | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-10-31
|  | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-10-31

## Green and Pond
RISK ASSESSMENT - GREEN AND POND 2023
Area | Items to Be Checked | 2023-01-03 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 2023-05-04 | 2023-06-01 | 2023-07-03 | 2023-07-31 | 2023-09-05 | 2023-10-04 | 2023-10-31 | Issue | Issue | Item Number | Date Notified | Date Resolved
GREEN | Hidden Potholes | bar: 2023-01-03 to 2023-10-31
Litter & Rubbish | bar: 2023-01-03 to 2023-10-31
Manhole Cover | bar: 2023-01-03 to 2023-10-31
Trees/Shrubs/Hedges | bar: 2023-01-03 to 2023-10-31
Grass Length | bar: 2023-01-03 to 2023-10-31
Spilt Rubbish By Bin | bar: 2023-01-03 to 2023-10-31
WOODS | Uneven Paths | [12 empty] | Monitoring of track for flooding continued, last flooded 28/2/2022 | GREEN 1 | 2022-02-28 | ON GOING | bar: 2023-01-03 to 2023-10-31
Overhanging Branches | bar: 2023-01-03 to 2023-10-31
Fallen Trees / Branches | bar: 2023-01-03 to 2023-10-31
Brambles / Nettles | bar: 2023-01-03 to 2023-10-31
Dropped Litter/ Rubbish | bar: 2023-01-03 to 2023-10-31
Wasps / Bee Nests | bar: 2023-01-03 to 2023-10-31
POND | Life Aid & Signage | [11 empty] | Signs Missing | Sign fallen off, reattached |  |  | 6/3/2023 JED | bar: 2023-01-03 to 2023-10-31
| Perimeter & Fence | [12 empty] | PPC to concider fencing pond as edges are very exposed, since rushes removed | GREEN 3 | 2023-09-05 | bar: 2023-01-03 to 2023-10-31
Trip/Slip/Fall Hazards | bar: 2023-01-03 to 2023-10-31
Gully Edges | bar: 2023-01-03 to 2023-10-31
| Brick Wall | [12 empty] | 2 loose bricks residents side, bricks removed |  | 2020-09-03 | 03/10/2023, MOP | bar: 2023-01-03 to 2023-10-31
Wooden area | bar: 2023-01-03 to 2023-10-31
Benches | Fit For Purpose | bar: 2023-01-03 to 2023-10-31
Bandstand | Electricity Supply Off/On | bar: 2023-01-03 to 2023-10-31
Electrics Undamaged | bar: 2023-01-03 to 2023-10-31
Fit To Use | bar: 2023-01-03 to 2023-10-31
| Path Safety | [12 empty] | Edge coming away, advisory, Risk 2 | GREEN 2 | 2020-09-03 | ON GOING | bar: 2023-01-03 to 2023-10-31
Bridge | Railings | bar: 2023-01-03 to 2023-10-31
Base Of Bridge | bar: 2023-01-03 to 2023-10-31
|  | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Benches | Safe To Use | bar: 2023-01-03 to 2023-10-31