## PROBLEMS AND RISK PRIORITY
Item Number | Unique ID | Problem | Priority | Proposed Action | PC informed | Date | Date resolved
| Playing field 1 | PPC shed resting on concerte blocks | RISK 2 | PPC aware, JB to arrange a permiment fix | 2023-09-05 | 2023-09-18
| Playing field 2 | Astro turf run up to practice nets badly split | RISK 2 | Cricket aware, cricket to repair | 01/06/2023, RJ
| Playing field 3 | Path round PAV crumbling, always had dips but deteriated over last month. | RISK 2 | Path to be patched, PC to manage. | 04/07/2023. RJ AND AE
| Playing field 4 | 4 loose slabs outside electrical room | RISK 2-3 | Hazzard taped, Slabs to re-concreted, PC to manage | 2023-07-04
4 | VH car park 1 | Parking bays | RISK 2 | Re mark - PC to manage | PPC | C/F | CIL?
| VH car park 2 | Loose slab by bridge | RISK 2 | To be recermented - JB aware and hopes to fix | 2023-07-04
6 | Green 1 | Track flooded, not into Kimber cottages | RISK 2 | VHM to momitor, flooded due to heavy rain, 4/12/2023 FIRST TWO COTTAGES GARDEN FLOODED, PPC INFORMED | 28/02/2022, 06/12/2023 | On going
9 | Green 2 | Edge coming away, advisory | RISK 2 | VHM to monitor | N.SATCHELL & PPC | On going
| Green 3 | Pond edge exposed since rushes have been removed | RISK 3 | PPC to consider if edge should be fenced. EXTRA DEEP WATER SIGNES ORDERED, LIFE BUOY TO BE ORDERED IN SPRING 2024 | 05/09/2023, 5/12/2023 | On going
| C/F = | ITEMS CARRIED FORWARD FOR OLD STYLE RA'S, PRE APRIL 2021
| RISK 1 | IMMPOBABLE
| RISK 2 | REMOTE
| RISK 3 | OCCASSIONAL (ACTION WITHIN 6 MONTHS)
| RISK 4 | PROBABLE (ACTION WITHIN 3 MONTHS)
| RISK 5 | HIGH RISK (IMMEDIATE ACTION)

## Allotments
RISK ASSESSMENT - ALLOTMENTS 2023 | [13 empty] | SUGGESTED EXAMPLES
Area | Items to Be Checked | 2023-01-03 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 2023-05-03 | 2023-06-01 | 2023-07-03 | 2023-07-31 | 2023-09-05 | 2023-10-03 | 2023-10-31 | 2023-12-05 | Issue | Item Number | Date Notified | Date Resolved
Main Footpaths | Hidden Potholes | bar: 2023-01-03 to 2023-10-31
Litter, Rubbish and General Waste | bar: 2023-01-03 to 2023-10-31
Obstructions | bar: 2023-01-03 to 2023-10-31
Raised Beds | Edges Clearly Visible | bar: 2023-01-03 to 2023-12-05
Water Butts | Check for Hazards | bar: 2023-01-03 to 2023-12-05
Wooded Area | Uneven Ground | bar: 2023-01-03 to 2023-12-05
Fallen Trees Branches | bar: 2023-01-03 to 2023-12-05
Overhanging Branches | bar: 2023-01-03 to 2023-12-05
Brambles / Nettles | bar: 2023-01-03 to 2023-12-05
Litter, Rubbish and General Waste | bar: 2023-01-03 to 2023-12-05
Wasp / Bee Nests | bar: 2023-01-03 to 2023-12-05
Stream | Warning Signs and Hazards | bar: 2023-01-03 to 2023-12-05
Bank Hazards | bar: 2023-01-03 to 2023-12-05
| Flooding | [12 empty] | FLOODED X 2, NO ACTION TAKEN BEGINNING DEC DUE TO HEAVY RAIN | bar: 2023-01-03 to 2023-12-05
Benches | Safe To Use | bar: 2023-01-03 to 2023-12-05
[8 empty] | ü | ü | ü | ü | ü | ü
Gates | Good Order | bar: 2023-01-03 to 2023-12-05

## Playing Field
RISK ASSESSMENT - PLAYING FIELD 2023
Area | Items to Be Checked | 2023-01-03 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 2023-05-03 | 2023-06-01 | 2023-07-03 | 2023-07-31 | 2023-09-05 | 2023-10-04 | 2023-10-31 | 2023-12-05 | Issue | Item number | Date Notified | Date Resolved
Field | Trips / Slip Hazard | [12 empty] | PPC SHED RESTING ON CONCRETE BLOCKS | Playing field 1 | 2023-09-18 | bar: 2023-01-03 to 2023-12-05
Litter On Field | Collect And Remove | [12 empty] | Bags of rubble by new archery shipping container |  | 2023-10-04 | 2023-12-07 | bar: 2023-01-03 to 2023-12-05
Cricket Square | Tap | bar: 2023-01-03 to 2023-12-05
General | bar: 2023-01-03 to 2023-12-05
Cricket Nets | General | [12 empty] | ASTRO TURF RUN UP SPLIT, KS AWARE | Playing field 2 | 2023-06-01 | bar: 2023-01-03 to 2023-12-05
Cricket Screen | Secured And Safe | bar: 2023-01-03 to 2023-12-05
Public Goals | Fit For Purpose | bar: 2023-01-03 to 2023-12-05
Club Goals | Posts / Nets | [12 empty] | GOALS REMOVED, BUT NEED SECURING |  | 2023-05-03 | NEW SEASON STARTED | bar: 2023-01-03 to 2023-12-05
Hedges / Trees | Overhanging Branches | bar: 2023-01-03 to 2023-12-05
Trees | Fallen Trees / Branches | bar: 2023-01-03 to 2023-12-05
All Areas | Brambles / Nettles | bar: 2023-01-03 to 2023-12-05
Litter / Hedges | Collect And Remove | bar: 2023-01-03 to 2023-12-05
Hedges / Trees | Wasp And Bee Nests | bar: 2023-01-03 to 2023-12-05
Pathways | Trip / Slip / Fall Hazards | [12 empty] | Path round PAV, is now crumbling, always had dips in it but deteriated over the last month. | Playing field 3 | 2023-07-04 | bar: 2023-01-03 to 2023-12-05
[14 empty] | 4 loose slabs outside electrical room, hazzard taped PPC aware, JB to look at. | Playing field 4 | 2023-07-04
Tennis Track | Signage Visible | bar: 2023-01-03 to 2023-12-05
| Detioration | [12 empty] | Cracked manhole, Specialised contractor to assess |  | C/F | 04/10/2023 C LEWERY | bar: 2023-01-03 to 2023-12-05
Passing bays in good order, installed 4/10/2023 | bar: 2023-10-04 to 2023-12-05
Benches x 2 | Fit For Purpose | bar: 2023-01-03 to 2023-12-05
Bkt Ball Court | Tarmac Safe | bar: 2023-01-03 to 2023-12-05
Litter Bins | Clear Overflowing Litter | bar: 2023-01-03 to 2023-12-05
Emptied On Schedule | bar: 2023-01-03 to 2023-12-05
Outbuildings | Vandalism | bar: 2023-01-03 to 2023-12-05

## Pavilion Car Park
RISK ASSESSMENT - PAVILION CAR PARK 2023
Area | Items to Be Checked | 2023-01-03 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 2023-05-04 | 2023-06-01 | 2023-07-03 | 2023-07-31 | 2023-09-05 | 2023-10-04 | 2023-10-04 | 2023-10-31 | 2023-12-05 | Issue | Item Number | Date Notified | Date Resolved
Car Park | Car Park Lighting | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Footpath Clear / Safe | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Signage Visible | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Trip Hazards | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Free From Litter | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Litter Bin Maintained | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Overhanging Branches | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Fallen Branches / Trees | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Bollards Safe | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Gates Safe And Locked, when not in use | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
| Recycling Compound | ü | ü | ü | û | ü | ü | û | ü | ü | û | ü | ü | ü

## Village Hall Car Park
RISK ASSESSMENT - VILLAGE HALL CAR PARK 2023
Area | Items to Be Checked | 03/0102023 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 04/05/023 | 2023-06-01 | 2023-07-03 | 2023-07-31 | 2023-09-05 | 2023-10-04 | 2023-10-31 | 2023-12-05 | Issue | Item number | Date Notified | Date Resolved
Car Park | Bay Marking | û | û | û | û | û | [7 empty] | Many faded, Risk 2 | VH car park 1 | 2019-11-01 | bar: 2023-06-01 to 2023-12-05
| Car Park Lighting | ü | ü | ü | ü | ü | [7 empty] | Loose slab by bridge | VH car park 2 | 2023-07-04 | bar: 2023-06-01 to 2023-12-05
| Footpath Clear / Safe | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-12-05
| Trip Hazards | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-12-05
| Hedges Safe | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-12-05
| Free From Litter | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-12-05
| Litter Bin Maintained | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-12-05
| Overhanging Branches | û | û | û | ü | ü | [7 empty] | Over hanging branches & brambles west border, cleared by working party |  | 2021-01-07 | 2023-03-18 | bar: 2023-06-01 to 2023-12-05
| Fallen Trees / Branches | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-12-05
|  | ü | ü | ü | ü | ü | bar: 2023-06-01 to 2023-12-05

## Green and Pond
RISK ASSESSMENT - GREEN AND POND 2023
Area | Items to Be Checked | 2023-01-03 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 2023-05-04 | 2023-06-01 | 2023-07-03 | 2023-07-31 | 2023-09-05 | 2023-10-04 | 2023-10-31 | 2023-12-05 | Issue | Issue | Item Number | Date Notified | Date Resolved
GREEN | Hidden Potholes | bar: 2023-01-03 to 2023-12-05
Litter & Rubbish | bar: 2023-01-03 to 2023-12-05
Manhole Cover | bar: 2023-01-03 to 2023-12-05
Trees/Shrubs/Hedges | bar: 2023-01-03 to 2023-12-05
Grass Length | bar: 2023-01-03 to 2023-12-05
Spilt Rubbish By Bin | bar: 2023-01-03 to 2023-12-05
WOODS | Uneven Paths | [13 empty] | Monitoring of track for flooding continued, last flooded 28/2/2022, FIRST 2 COTTAGES GARDEN FLOODED 4/12/2023 PPC INFORMED | GREEN 1 | 2022-02-28 | ON GOING | bar: 2023-01-03 to 2023-12-05
Overhanging Branches | bar: 2023-01-03 to 2023-12-05
Fallen Trees / Branches | bar: 2023-01-03 to 2023-12-05
Brambles / Nettles | bar: 2023-01-03 to 2023-12-05
Dropped Litter/ Rubbish | bar: 2023-01-03 to 2023-12-05
Wasps / Bee Nests | bar: 2023-01-03 to 2023-12-05
POND | Life Aid & Signage | [12 empty] | Signs Missing | Sign fallen off, reattached |  |  | 6/3/2023 JED | bar: 2023-01-03 to 2023-12-05
| Perimeter & Fence | [13 empty] | PPC to concider fencing pond as edges are very exposed, since rushes removed | GREEN 3 | 2023-09-05 | bar: 2023-01-03 to 2023-12-05
Trip/Slip/Fall Hazards | bar: 2023-01-03 to 2023-12-05
Gully Edges | bar: 2023-01-03 to 2023-12-05
| Brick Wall | [13 empty] | 2 loose bricks residents side, bricks removed |  | 2020-09-03 | 03/10/2023, MOP | bar: 2023-01-03 to 2023-12-05
Wooden area | bar: 2023-01-03 to 2023-12-05
Benches | Fit For Purpose | bar: 2023-01-03 to 2023-12-05
Bandstand | Electricity Supply Off/On | bar: 2023-01-03 to 2023-12-05
Electrics Undamaged | bar: 2023-01-03 to 2023-12-05
Fit To Use | bar: 2023-01-03 to 2023-12-05
| Path Safety | [13 empty] | Edge coming away, advisory, Risk 2 | GREEN 2 | 2020-09-03 | ON GOING | bar: 2023-01-03 to 2023-12-05
Bridge | Railings | bar: 2023-01-03 to 2023-12-05
Base Of Bridge | bar: 2023-01-03 to 2023-12-05
|  | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Benches | Safe To Use | bar: 2023-01-03 to 2023-12-05